## Start Here
AI-READY PDLC ¦ Jira Cloud Configuration Matrix
Version 1.0 • Company-managed projects • 23 October 2026 • Proposed, not live configuration
Configuration element | Design quantity
Work types | 14
Reusable workflows | 8
Custom field definitions | 45
Controlled transition examples | 45
Standard screens | 15
Screen schemes | 8
IMPLEMENTATION NOTES
Authoritative narrative: PDLC_Jira_Cloud_Blueprint.md. The workbook is a build/QA matrix for Jira administrators.
The design uses PTS as portfolio book of record, Jira as lifecycle work register, and enterprise ITSM/CI/CD/GRC as other authoritative systems.
Core 14-type hierarchy is Epic > standard issue > Sub-task; optional levels above Epic require supported licensing and a separately reviewed hierarchy change.
Every table is proposed design. Validate against the tenant’s Jira edition, current Field schemes experience, existing app capabilities and enterprise policies.
No native Jira import is supplied: workflow validators, screen schemes, issue security and policy gates require implementation and user-acceptance testing.
P0/P1/P2 are rollout phases, not indiscriminately mandatory field configuration settings. Transition-specific checks define actual requiredness.

## Issue Types
Issue Types ¦ PDLC v1.0
Design source: Section 2. Work type hierarchy. Confirm tenant-specific support before implementation.
ID | Work type | Hierarchy | Typical owner | Required purpose / usage | Workflow
IT01 | Epic | 1 | Product / delivery lead | Business capability, material product change, delivery outcome, multi-workstream package | WF01-Outcome
IT02 | Story | 0 | Product owner / engineer | Increment of user/business value with verifiable acceptance criteria | WF02-Delivery
IT03 | Enabler | 0 | Engineering / architecture lead | Platform, architecture, data or security work enabling outcomes | WF02-Delivery
IT04 | Technical Debt | 0 | Engineering lead | Deliberate remediations improving maintainability, reliability or lifecycle health | WF02-Delivery
IT05 | Task | 0 | Assigned practitioner | Bounded delivery or operational work that is not a Story | WF03-Task
IT06 | Spike | 0 | Engineer / analyst | Timeboxed investigation, hypothesis and recorded findings | WF03-Task
IT07 | Governance Action | 0 | Control/delivery owner | Required remediation of a governance or assurance finding | WF03-Task
IT08 | Sub-task | -1 | Assigned practitioner | Optional execution breakdown of a Story, Task, Bug or other supported parent | WF03-Task
IT09 | Bug | 0 | Engineering / quality owner | Reproducible defect in software, data or infrastructure-as-code | WF04-Defect
IT10 | Risk | 0 | Named risk owner | Potential future condition; likelihood, impact, treatment, residual acceptance | WF05-Risk
IT11 | Impediment | 0 | Delivery owner | Current blocker needing removal; not a speculative risk | WF05-Risk
IT12 | Dependency | 0 | Dependency owner | Explicit cross-team or external deliverable, commitment and need-by date | WF06-Dependency
IT13 | Decision | 0 | Decision authority | Consequential architectural, business or delivery decision with rationale | WF07-Decision
IT14 | Control Exception | 0 | Designated control owner | Formal time-limited deviation to an approved control, with authority and expiry | WF08-Exception

## Native Fields
Native Fields ¦ PDLC v1.0
Design source: Section 3. Standard field dictionary. Confirm tenant-specific support before implementation.
Field | Type | Scope | Mandatory at creation | Ownership / notes
Summary | Native text | All | Yes | Concise deliverable / decision / risk statement
Description | Native rich text | All | Yes, short at intake | Structured issue template varies by work type
Reporter | Native user | All | Auto | Jira user/automation identity
Assignee | Native user | All | No | Required at Ready / active treatment / assigned decision stage
Parent | Native parent | Standard / Sub-task | As appropriate | Parent Epic recommended for delivery types; parent required for Sub-task
Priority | Native priority | All | Default P2 | Never mix with regulatory/materiality risk tier
Labels | Native labels | All | No | Only non-critical categorisation; avoid use as primary controls
Components | Native component(s) | Delivery / Bug | No | Existing technical component ownership
Fix Version/s | Native version | Delivery / Bug | No | Set by Ready for Release where relevant
Affects Version/s | Native version | Bug | No | Where known
Linked work items | Native links | All | No | Blocks, relates to, caused by, implements, mitigates
Due date | Native date | Risk / Action / Dependency | At active assignment | Not equivalent to approved PTS baseline
Original estimate / time tracking | Native | Delivery | Optional | Use consistently or omit; not an AI productivity proxy
Sprint | Native Agile field | Scrum delivery teams only | No | Optional; Kanban and flow-based groups need not use sprints
Resolution | Native resolution | All | Never | Populated only at terminal transition; cleared on reopening
Attachment / comments | Native | All | No | No secrets, sensitive model inputs or uncontrolled confidential artefacts

## Custom Fields
Custom Fields ¦ PDLC v1.0
Design source: Section 4. Custom field dictionary. Confirm tenant-specific support before implementation.
Code | Custom field | Jira field type | Applies to | Gate / obligation | Source or stewardship | Phase
CF01 | Portfolio / PTS Initiative ID | Short text | Epic | Before Approved if portfolio governed | PTS reference, validated | P0
CF02 | PTS Milestone ID | Short text | Epic, Dependency | Before commitment claim; optional on work not linked to a milestone | PTS read-only sync | P1
CF03 | Product / Service ID | Short text / approved Assets reference | Epic, Story, Enabler, Bug, Technical Debt | Before Ready or assessment closure | CMDB / service inventory | P0
CF04 | Business Owner | User picker | Epic, Story | Before Epic approval / Story Ready | Named accountable human | P0
CF05 | Delivery Lead | User picker | Epic, Dependency | Before Epic approval | Named accountable human | P0
CF06 | Engineering Lead | User picker | Epic, Enabler, Technical Debt, Bug | Before Ready / active delivery | Named accountable human | P1
CF07 | Business Outcome | Paragraph | Epic | Before approval | Product / business owner | P0
CF08 | Success Measure | Paragraph | Epic | Before approval; measurable baseline/target | Product owner | P1
CF09 | Technology Domain | Single select | Epic, all standard work | At creation or inherited | Risk, Capital, Markets/FO, Shared | P0
CF10 | Delivery Change Type | Single select | Epic, Story, Enabler, Task, Bug | Before Ready | Application, Infrastructure, Data, Model, Security, Control | P0
CF11 | Change Risk Tier | Single select | Epic, delivery types, Bug | Before Ready; re-evaluate on material changes | T1, T2, T3, T4; policy owner | P0
CF12 | Data Classification | Single select | Epic, delivery types | Before Ready if data in scope | Approved classification, not free text | P1
CF13 | Critical Service Impact | Single select | Epic, delivery types | Before Ready | Yes, No, Unknown (Unknown blocks relevant gates) | P1
CF14 | Regulatory Driver | Single select | Epic, Story, Enabler | When applicable | None, Regulatory, CO/Remediation, Internal Control, Other | P1
CF15 | Acceptance Criteria | Paragraph | Story, Enabler, Technical Debt, Bug | Before Ready / triage acceptance | Business and engineering reviewers | P0
CF16 | Delivery Method | Single select | Epic | Before In Delivery | Scrum, Kanban, Hybrid, Milestone-led | P2
CF17 | Execution Mode | Single select | Story, Enabler, Task, Spike, Bug | Before AI execution; default Human | Human, AI-Assisted, Supervised Agent, Policy-Autonomous | P0
CF18 | Human Accountable Owner | User picker | AI-enabled work types | Before agent run | Named bank employee | P0
CF19 | Approved Agent ID | Short text | AI-enabled work types | Before agent execution | Agent registry reference | P1
CF20 | Latest Agent Run Reference | URL / short text | AI-enabled work types | System-populated; never required for manual | Agent execution platform | P1
CF21 | Agent Run Outcome | Single select | AI-enabled work types | System only | Not Started, Running, Completed, Failed, Cancelled | P1
CF22 | Control Profile ID | Short text | Epic, delivery types, Bug, Control Exception | Before Ready; inherited / overridden by policy | Central control catalogue | P0
CF23 | Control Evaluation Status | Single select | Epic, delivery types, Bug | System only | Not Evaluated, Passed, Failed, Missing Evidence, Approved Exception, Stale | P0
CF24 | Evidence Package Reference | URL / short text | Delivery types, Bug, Governance Action, Control Exception | Before validation / closure | Evidence service; immutable/versioned references | P1
CF25 | Independent Validation Required | Single select | Epic, Story, Enabler, Bug | Before Ready when material | Yes, No, Assessment Pending | P1
CF26 | Release Gate Status | Single select | Story, Enabler, Bug, Technical Debt | System only before release | Not Evaluated, Allowed, Blocked, Exception | P1
CF27 | Defect Severity | Single select | Bug | At triage | S1 Critical, S2 High, S3 Medium, S4 Low | P0
CF28 | Environment Affected | Single select | Bug | At triage | Dev, Test, UAT, Preprod, Production, Multiple | P1
CF29 | Reproduction / Diagnostic Reference | URL / paragraph | Bug | Before in-progress for reproducible bugs | QA/repository evidence | P1
CF30 | Risk Likelihood | Single select | Risk | Before treatment | 1–5 calibrated definitions | P0
CF31 | Risk Impact | Single select | Risk, Impediment | Before treatment | 1–5 calibrated definitions | P0
CF32 | Risk Treatment / Mitigation Plan | Paragraph | Risk, Impediment | Before Treatment | Named risk owner | P0
CF33 | Dependency Owning Team | Short text / team reference | Dependency | Before Acknowledged | Team catalogue | P0
CF34 | Dependency Need-By Date | Date | Dependency | Before Acknowledged | Receiving team | P0
CF35 | Dependency Commitment Date | Date | Dependency | Before In Progress | Supplying team | P1
CF36 | Decision Authority | User picker | Decision | Before Awaiting Decision | Accountable authorised role | P0
CF37 | Decision Rationale | Paragraph | Decision | Before Decided | Decision authority | P0
CF38 | Control ID | Short text | Control Exception, Governance Action | Before assessment | GRC authoritative reference | P0
CF39 | Exception Justification | Paragraph | Control Exception | Before Awaiting Approval | Requestor | P0
CF40 | Exception Approver | User picker | Control Exception | Before Awaiting Approval | Control owner / authorised delegate | P0
CF41 | Exception Expiry | Date | Control Exception | Before Approved Active | Time-boxed approved date | P0
CF42 | Compensating Controls | Paragraph / URL | Control Exception | Before Approved Active | Control owner/evidence service | P1
CF43 | Resolution / Outcome Evidence | URL / paragraph | Risk, Dependency, Decision, Governance Action, Spike | Before Closed/Done | Owning function | P1
CF44 | ITSM Change Record ID | Short text | Epic, Story, Enabler, Bug | When production change in scope, before authorised release | ITSM authoritative | P1
CF45 | Data Freshness Timestamp | Date-time (external / app) | Epic / work | System only | Source integration / assurance platform | P2

## Workflow Mapping
Workflow Mapping ¦ PDLC v1.0
Design source: Section 5. Workflow scheme. Confirm tenant-specific support before implementation.
Work type | Workflow key | Normal route | Terminal resolution
Epic | WF01-Outcome | Proposed → Assessing → Awaiting Approval → Approved → In Delivery → Outcome Review → Closed | Done / Cancelled / Rejected
Story | WF02-Delivery | Backlog → Refining → Ready → In Progress → In Review → In Validation → Ready for Release → Done | Done / Cancelled
Enabler | WF02-Delivery | Backlog → Refining → Ready → In Progress → In Review → In Validation → Ready for Release → Done | Done / Cancelled
Technical Debt | WF02-Delivery | Backlog → Refining → Ready → In Progress → In Review → In Validation → Ready for Release → Done | Done / Cancelled
Task | WF03-Task | To Do → In Progress → In Review → Done | Done / Cancelled
Spike | WF03-Task | To Do → In Progress → In Review → Done | Done / Cancelled
Governance Action | WF03-Task | To Do → In Progress → In Review → Done | Done / Cancelled
Sub-task | WF03-Task | To Do → In Progress → In Review → Done | Done / Cancelled
Bug | WF04-Defect | Reported → Triaged → In Progress → In Validation → Resolved | Fixed / Duplicate / Won't Fix / Cannot Reproduce
Risk | WF05-Risk | Open → Assessing → Treatment → Monitoring → Closed | Mitigated / Accepted / Transferred / No Longer Applicable
Impediment | WF05-Risk | Open → Assessing → Treatment → Monitoring → Closed | Resolved / No Longer Applicable
Dependency | WF06-Dependency | Identified → Acknowledged → In Progress → Satisfied → Closed | Satisfied / Superseded / Cancelled
Decision | WF07-Decision | Proposed → Analysis → Awaiting Decision → Decided → Recorded | Decided / Rejected / Superseded
Control Exception | WF08-Exception | Raised → Assessed → Awaiting Approval → Approved Active → Remediation → Verified → Closed | Remediated / Rejected / Withdrawn

## Statuses
Statuses ¦ PDLC v1.0
Design source: Section 6. Workflow status. Confirm tenant-specific support before implementation.
Workflow | Status | Category | Purpose
WF01-Outcome | Proposed | To Do | New outcome awaiting initial evaluation
WF01-Outcome | Assessing | In Progress | Scope, benefits, control impact analysed
WF01-Outcome | Awaiting Approval | In Progress | Submitted to decision authority
WF01-Outcome | Approved | To Do | Authorised but not started
WF01-Outcome | In Delivery | In Progress | Work underway
WF01-Outcome | Outcome Review | In Progress | Outcomes/control evidence being assessed
WF01-Outcome | Closed | Done | Outcome formally concluded
WF01-Outcome | On Hold | In Progress | Temporarily paused with explicit reason
WF01-Outcome | Rejected | Done | Demand rejected with rationale
WF01-Outcome | Cancelled | Done | Approved/active outcome cancelled
WF02-Delivery | Backlog | To Do | Captured, not refined
WF02-Delivery | Refining | In Progress | Requirement, dependencies and policy review
WF02-Delivery | Ready | To Do | Ready criteria satisfied
WF02-Delivery | In Progress | In Progress | Human/agent implementation underway
WF02-Delivery | In Review | In Progress | Peer or design review
WF02-Delivery | In Validation | In Progress | Required tests, assurance and acceptance
WF02-Delivery | Ready for Release | In Progress | Delivery package verified, awaiting controlled release
WF02-Delivery | Done | Done | Accepted outcome completed and evidenced
WF02-Delivery | Cancelled | Done | Work withdrawn with authorisation
WF03-Task | To Do | To Do | Action created
WF03-Task | In Progress | In Progress | Action underway
WF03-Task | In Review | In Progress | Output being reviewed
WF03-Task | Done | Done | Review accepted
WF03-Task | Cancelled | Done | Work withdrawn
WF04-Defect | Reported | To Do | New alleged defect
WF04-Defect | Triaged | To Do | Severity, ownership, reproduction assessed
WF04-Defect | In Progress | In Progress | Fix underway
WF04-Defect | In Validation | In Progress | Fix being retested
WF04-Defect | Resolved | Done | Fix verified or closed with disposition
WF05-Risk | Open | To Do | New risk or impediment
WF05-Risk | Assessing | In Progress | Analysis, ownership and treatment selection
WF05-Risk | Treatment | In Progress | Mitigation/clearance underway
WF05-Risk | Monitoring | In Progress | Treatment complete, residual exposure monitored
WF05-Risk | Closed | Done | Resolved or formally accepted
WF06-Dependency | Identified | To Do | Dependency proposed
WF06-Dependency | Acknowledged | To Do | Supplying team accepts ownership
WF06-Dependency | In Progress | In Progress | Supplier delivering
WF06-Dependency | Satisfied | In Progress | Receiver validates deliverable
WF06-Dependency | Closed | Done | Receiver has accepted evidence
WF07-Decision | Proposed | To Do | Decision needed
WF07-Decision | Analysis | In Progress | Options/tradeoffs compiled
WF07-Decision | Awaiting Decision | In Progress | Authorised approver needed
WF07-Decision | Decided | In Progress | Authority selected path
WF07-Decision | Recorded | Done | Rationale, owner, actions recorded
WF07-Decision | Rejected | Done | Proposal refused
WF08-Exception | Raised | To Do | Exception requested
WF08-Exception | Assessed | In Progress | Control impact and mitigation assessed
WF08-Exception | Awaiting Approval | In Progress | Awaiting independent authority
WF08-Exception | Approved Active | In Progress | Temporary authorisation in force
WF08-Exception | Remediation | In Progress | Underlying issue being corrected
WF08-Exception | Verified | In Progress | Control owner verifies evidence
WF08-Exception | Expired | In Progress | Exception expired, control evaluation must fail/block unless separately authorised
WF08-Exception | Closed | Done | Remediation complete and exception closed
WF08-Exception | Rejected | Done | No permission granted

## Transitions
Transitions ¦ PDLC v1.0
Design source: Section 7. Transition and gate. Confirm tenant-specific support before implementation.
ID | Workflow | From | Transition / To | Mandatory validation or policy | Authorised role | Mechanism
TR01 | WF01-Outcome | Proposed | Start Assessment → Assessing | Summary, description, owner assigned | Product / Delivery Lead | Native
TR02 | WF01-Outcome | Assessing | Submit for Approval → Awaiting Approval | PTS ID where relevant, Business Outcome, Business Owner, Delivery Lead, risk assessment | Product Owner | Native + Policy
TR03 | WF01-Outcome | Awaiting Approval | Approve → Approved | Named approver, investment authority in PTS, decision reference | Portfolio Approver | Human + Policy
TR04 | WF01-Outcome | Awaiting Approval | Reject → Rejected | Rejection rationale, Resolution=Rejected | Portfolio Approver | Native + Human
TR05 | WF01-Outcome | Approved | Begin Delivery → In Delivery | Named Engineering Lead, epic work decomposed, controls profile assigned | Delivery Lead | Native + Policy
TR06 | WF01-Outcome | In Delivery | Begin Outcome Review → Outcome Review | Required children resolved or managed explicitly, outcome evidence present | Delivery Lead | Policy
TR07 | WF01-Outcome | Outcome Review | Close Outcome → Closed | Business owner accepts outcome, portfolio record reconciled, Resolution=Done | Product / Portfolio Approver | Human + Policy
TR08 | WF02-Delivery | Backlog | Refine → Refining | Named accountable lead where needed | Product/Engineering | Native
TR09 | WF02-Delivery | Refining | Mark Ready → Ready | Acceptance Criteria, service ID, risk tier, change type, owner, control profile, dependency review | Product + Engineering | Native + Policy
TR10 | WF02-Delivery | Ready | Start Work → In Progress | Team capacity, applicable authorisations; approved agent identity for autonomous run | Engineering Lead / Assignee | Native + Policy
TR11 | WF02-Delivery | In Progress | Submit Review → In Review | Code/design reference; work output attached/linked | Assignee | Native
TR12 | WF02-Delivery | In Review | Start Validation → In Validation | Peer review outcome recorded; approved build/evidence references | Engineering / Reviewer | Policy
TR13 | WF02-Delivery | In Validation | Mark Release Ready → Ready for Release | Required tests passed, control status acceptable under policy, no unauthorised open S1 defects, validation evidence | Quality / Engineering | Policy
TR14 | WF02-Delivery | Ready for Release | Complete → Done | ITSM change when applicable, release/acceptance evidence, human owner acceptance, Resolution=Done | Product/Delivery Owner | Human + Policy
TR15 | WF02-Delivery | In Review or In Validation | Rework → In Progress | Record reasons; invalidate stale evidence | Reviewer/QA | Policy
TR16 | WF03-Task | To Do | Start → In Progress | Owner assigned; agent policy check if agent-executed | Assignee | Native + Policy
TR17 | WF03-Task | In Progress | Submit Review → In Review | Work output recorded; Spike requires findings | Assignee | Native
TR18 | WF03-Task | In Review | Complete → Done | Acceptance by reviewer; governance action may require evidence; Resolution=Done | Reviewer / Control Owner | Native + Human
TR19 | WF04-Defect | Reported | Triage → Triaged | Severity, affected env, service, reproduce/evidence or triage disposition | QA / Engineering | Native
TR20 | WF04-Defect | Triaged | Begin Fix → In Progress | Owner, remediation priority, linked affected work/release | Engineering Lead | Native
TR21 | WF04-Defect | In Progress | Submit Retest → In Validation | Fix reference, deployment to test, tests | Engineer | Policy
TR22 | WF04-Defect | In Validation | Resolve → Resolved | Retest pass OR authorised closure disposition, Resolution correctly set | QA / Product Owner | Policy + Human
TR23 | WF04-Defect | Resolved | Reopen → Triaged | Reproduction/escaped defect reference, clear Resolution | QA / Product Owner | Native + Policy
TR24 | WF05-Risk | Open | Assess → Assessing | Named owner, explanation of event/threat | Delivery / Risk Owner | Native
TR25 | WF05-Risk | Assessing | Start Treatment → Treatment | Likelihood/impact for Risk, severity for Impediment, treatment plan, due date | Risk Owner | Native
TR26 | WF05-Risk | Treatment | Monitor → Monitoring | Treatment evidence, residual assessment | Risk Owner | Human
TR27 | WF05-Risk | Monitoring | Close → Closed | Evidence + authorised acceptance of residual risk, Resolution | Risk Owner / Approver | Human + Policy
TR28 | WF06-Dependency | Identified | Acknowledge → Acknowledged | Supplying team, receiving team, need-by date, named owner | Supplier Lead | Human
TR29 | WF06-Dependency | Acknowledged | Start Delivery → In Progress | Supplier commitment date and planned deliverable | Supplier Lead | Native
TR30 | WF06-Dependency | In Progress | Submit Fulfilment → Satisfied | Delivered artifact/evidence and version | Supplier Lead | Policy
TR31 | WF06-Dependency | Satisfied | Accept → Closed | Receiver verifies deliverable and outcome, Resolution | Receiving Lead | Human
TR32 | WF07-Decision | Proposed | Analyse → Analysis | Question and context | Decision Requestor | Native
TR33 | WF07-Decision | Analysis | Request Decision → Awaiting Decision | Options, tradeoffs, Decision Authority | Requestor | Native
TR34 | WF07-Decision | Awaiting Decision | Decide → Decided | Authenticated authority, rationale and decision | Decision Authority | Human + Native
TR35 | WF07-Decision | Decided | Record → Recorded | Decision reference, impacts, linked follow-up actions | Decision Owner | Policy
TR36 | WF08-Exception | Raised | Assess → Assessed | Control ID, request justification, requester identity | Control Owner | Native
TR37 | WF08-Exception | Assessed | Request Approval → Awaiting Approval | Compensating controls, expiry, approver, residual risk assessment | Control Owner | Policy
TR38 | WF08-Exception | Awaiting Approval | Approve → Approved Active | Independent authorised approver (not requestor), expiry in future, decision record; no Resolution | Control Approver | Human + Policy
TR39 | WF08-Exception | Awaiting Approval | Reject → Rejected | Reason; Resolution=Rejected | Control Approver | Human + Native
TR40 | WF08-Exception | Approved Active | Start Remediation → Remediation | Remediation owner and target | Action Owner | Native
TR41 | WF08-Exception | Approved Active | Expire → Expired | Expiry passed, disallow unauthorised control bypass | Policy Service | Policy
TR42 | WF08-Exception | Remediation | Verify → Verified | Independent verification package | Control Validator | Human + Policy
TR43 | WF08-Exception | Verified | Close → Closed | Validation acceptance, GRC reference update, Resolution=Remediated | Control Owner | Human + Policy
TR44 | All non-terminal | Appropriate state | Cancel → Cancelled / Rejected | Appropriate approver + reason; do not skip retained records | Product/Control owner | Human
TR45 | All terminal (where permitted) | Done/Closed/Recorded/Resolved | Reopen → appropriate active state | Reason, invalidate controls, clear Resolution, preserve audit trail | Authorised owner | Native + Policy

## Screens
Screens ¦ PDLC v1.0
Design source: Section 8. Screen catalogue. Confirm tenant-specific support before implementation.
ID | Screen / layout | Used for | Suggested tab groups and fields
SCR01 | PDLC-Epic-Create | Epic create | Summary, Description, Product/Service, Technology Domain, Business Owner, Business Outcome, Reporter, Priority
SCR02 | PDLC-Epic-Edit | Epic edit | Overview; Accountability; Portfolio & Outcome; Delivery & Dependencies; Governance; Evidence
SCR03 | PDLC-Delivery-Create | Story, Enabler, Debt | Summary, Description, Parent/Epic, Assignee, Service, Change Type, Acceptance Criteria, Priority
SCR04 | PDLC-Delivery-Edit | Story, Enabler, Debt | Requirements; Engineering; Validation; Governance; AI Execution References; Links
SCR05 | PDLC-Task-CreateEdit | Task, Spike, Governance Action, Sub-task | Summary, Description, Parent where relevant, Assignee, Due date, review/evidence
SCR06 | PDLC-Bug-CreateEdit | Bug | Summary, Steps to reproduce, expected/actual result, Severity, Environment, Service, Version, Evidence
SCR07 | PDLC-Risk-CreateEdit | Risk, Impediment | Summary, event/impact, likelihood (risk), impact, owner, mitigation, due date, links
SCR08 | PDLC-Dependency-CreateEdit | Dependency | Dependency promise, supplier/receiver, Need-By, Commitment, links, evidence
SCR09 | PDLC-Decision-CreateEdit | Decision | Question, options, trade-offs, decision authority, rationale, date, actions
SCR10 | PDLC-Exception-CreateEdit | Control Exception | Control ID, justification, compensating controls, expiry, approver, evidence
SCR11 | PDLC-Review-Transition | Work review/rework | Reviewer, review outcome / comments, evidence reference
SCR12 | PDLC-Approval-Transition | Epic, Decision, Exception | Decision authority, rationale, date; only appropriate fields for each transition
SCR13 | PDLC-Validation-Transition | Deliverable/Defect | Evidence reference, acceptance outcome, residual defects, test record links
SCR14 | PDLC-Closure-Transition | All controlled closure | Resolution (where designed), closure evidence, decision/comments
SCR15 | PDLC-View-Layout | All | Group fields into Overview / Ownership / Delivery / Assurance / AI / History; display system-derived fields without user edit permissions

## Screen Schemes
Screen Schemes ¦ PDLC v1.0
Design source: Section 8. Screen catalogue. Confirm tenant-specific support before implementation.
Screen scheme | Work types | Create screen | Edit screen | View layout
SS01-Epic | Epic | SCR01 | SCR02 | SCR15
SS02-Delivery | Story, Enabler, Technical Debt | SCR03 | SCR04 | SCR15
SS03-Task | Task, Spike, Governance Action, Sub-task | SCR05 | SCR05 | SCR15
SS04-Bug | Bug | SCR06 | SCR06 | SCR15
SS05-Risk | Risk, Impediment | SCR07 | SCR07 | SCR15
SS06-Dependency | Dependency | SCR08 | SCR08 | SCR15
SS07-Decision | Decision | SCR09 | SCR09 | SCR15
SS08-Exception | Control Exception | SCR10 | SCR10 | SCR15

## Field Gates
Field Gates ¦ PDLC v1.0
Design source: Section 9. Field configuration. Confirm tenant-specific support before implementation.
Field group | Create requirement | Ready / assessment gate | Close / release gate
Common minimum | Summary; Description; work type; Reporter | Assignee/owner, parent where relevant | Resolution and closure rationale
Epic | Business intent | PTS where governed; Business Owner; Outcome; Risk Tier; Control Profile | Business acceptance; outcome/evidence; reconcile portfolio
Story/Enabler/Debt | Description; short outcome | Service; Risk Tier; Acceptance Criteria; Owner; Control Profile | Peer review; tests; required evidence, human acceptance
Bug | Description; impact | Severity; service; environment/triage; reproducibility | Verified fix or authorised disposition
Risk/Impediment | Event/problem; owner | Rating/treatment/impact/date | Acceptance and evidence
Dependency | Producer/receiver description | Supplier acknowledgement and need-by | Receiving-team acceptance
Decision | Question/context | Options, named authority | Rationale and follow-up references
Exception | Control ID and reason | Approver, compensating controls, expiry | Verified remediation and controls record

## Link Types
Link Types ¦ PDLC v1.0
Design source: Section 10. Links, dependencies. Confirm tenant-specific support before implementation.
Link name | Outward | Inward | Use
Blocks (native preferred) | blocks | is blocked by | True sequence/impact relationship
Relates to (native) | relates to | relates to | General relationship, not a dependency metric
Implements Control | implements control for | is implemented by | Work linked to Governance Action/Control reference where approved
Mitigates Risk | mitigates | is mitigated by | Task/epic controls exposure
Depends on External | depends on | is needed by | Only if no satisfactory native relationship; ensure Plans semantics
Supersedes | supersedes | is superseded by | Decision/change replacement lineage

## Roles and Authority
Roles and Authority ¦ PDLC v1.0
Design source: Section 11. Workflow enforcement. Confirm tenant-specific support before implementation.
Function | May create | May transition | May approve | Must not do
Product Owner | Epic, Story, Decision | Demand, acceptance | Business acceptance within delegation | Override independent security/model approval
Delivery Lead / PM | Epic, Dependency, Risk, Action | Planning, delivery management | Management escalation/operational decisions | Approve own exception without delegation
Engineering Lead | Work, Bug, Enabler | Engineering lifecycle | Technical peer review per policy | Override release/security gates
Contributor / Engineer | Story, Task, Bug, Spike | Assigned execution stages | Peer review only when independent | Administer protected schemes
Quality / Independent Validator | Bug, QA actions | Validation states | Test/verification sign-off | Be sole author and validator for required independent gates
Control Owner / Approver | Risk, Exception, Action | Control assessment | Exception/risk acceptance when authorised | Delegate to unapproved bot or requestor
Portfolio Approver | Epic/Decision | Approval/closure | Investment/milestone decisions | Replace PTS record by Jira edit
Integration / Agent Service | Controlled API actions | Specifically allowed service transitions | **Never autonomously accept material risk** | Browse all projects by default, set closure permissions broadly
Jira Administrator | Scheme administration | Admin-only maintenance | No implied business approval | Use admin power as substitute for separation of duties
Read-only Audit / Governance | As policy allows | None | None | Modify source evidence

## Automation
Automation ¦ PDLC v1.0
Design source: Section 12. Automation. Confirm tenant-specific support before implementation.
Rule | Trigger | Behaviour | Guard / failure behaviour | Priority
AU01 | Epic created | Validate/reference PTS ID; import authorised metadata | Never overwrite approved PTS commitment from Jira | P0
AU02 | Parent/owner changed | Propagate Service/Domain where allowed; detect mismatch | Do not override explicit approved exceptions | P0
AU03 | Move to Ready | Request synchronous control profile evaluation | If unavailable, fail closed at actual release gate | P0
AU04 | Flagged / blocks link | Notify accountable dependency owner and track aging | Deduplicate alerts; no auto-escalation without thresholds | P0
AU05 | PR created/updated | Link commits/PRs to issue; update engineering activity | Repository permission boundary; avoid direct status assumption | P1
AU06 | CI build/test completed | Record source evidence reference and outcome | Ignore unverifiable results; map run/commit IDs | P1
AU07 | Control evidence updated | Re-evaluate profile and mark Passed/Failed/Missing/Stale | External evaluator authoritative; no LLM pass/fail | P0
AU08 | Evidence outdated by code change | Invalidate prior readiness where applicable | Block unsupported reuse of stale testing evidence | P1
AU09 | Agent requested | Confirm allowed execution mode, identity, owner and authorisation | Reject unregistered agents or sensitive scope | P1
AU10 | Agent run completed | Record run reference/outcome; create human review task if required | Never auto-mark issue Done from agent success alone | P1
AU11 | Exception approved | Record approval/expiry; schedule expiry watch | Keep exception open; never mark control as Passed | P0
AU12 | Exception expiry reached | Transition to Expired; revoke permitted bypass and notify | Run via policy service; avoid time lag as sole safeguard | P0
AU13 | Risk impact/date worsens | Re-evaluate severity and alert risk owner | No autonomous acceptance/escalation of policy decisions | P1
AU14 | PTS milestone variance found | Generate evidence-linked anomaly / recommendation | Do not unilaterally change PTS baseline or RAG | P1
AU15 | Planned closure | Collect acceptance + evidence + source reconciliation | Do not set Resolution until actual transition succeeds | P0
AU16 | Service/source unavailable | Mark source freshness degraded and findings as unverified | No silent `Green` or `Passed` by default | P0

## Risk Tiers
Risk Tiers ¦ PDLC v1.0
Design source: Section 13. Definition of Ready. Confirm tenant-specific support before implementation.
Tier | Example | Indicative lifecycle gate | Agent autonomy ceiling (proposed)
T1 Low | Internal, reversible, non-sensitive minor update | Standard automated checks, approved standard change pattern | Policy-Autonomous for specifically authorised actions
T2 Standard | Routine service functionality | Peer review, test evidence, release control | Supervised Agent; selective policy automation
T3 Material | Critical data processing/integration | Named business/engineering/quality approvals, enhanced controls | Supervised Agent in nonproduction; human release decision
T4 Critical / Regulated | Material capital model, trading controls, regulatory submissions | Applicable independent challenge, extensive evidence, formal change authority | Advisory or supervised bounded tasks; no agent risk acceptance

## Delivery Views
Delivery Views ¦ PDLC v1.0
Design source: Section 14. Board, portfolio. Confirm tenant-specific support before implementation.
View | Target audience | Columns / filters / insight
Team Flow Board | Engineers / product | Backlog, Ready, In Progress, In Review, In Validation, Ready for Release, Done; flagged blocked
Defect Triage | QA / service teams | Reported, Triaged, In Progress, In Validation, Resolved; S1/S2 and reopened filters
Risk & Dependency | PM, programme, PMO | Risk exposure, open impediments, external dependencies, need-by vs commitment variance
Controls Workbench | Control owners / assurance | Missing evidence, failing controls, approved active exceptions, expiries, stale results
Agent Work Monitoring | Engineering/platform | Agent run references, failure, waiting human review, tasks by execution mode; underlying runs outside Jira
Portfolio Assurance | PMO / Directors | PTS-linked outcomes, epic health, milestone exceptions, validation gaps, decision queue
Migration / Governance | Jira governance | Scheme adoption, mapping errors, custom field duplication, automation failures, version compliance

## Build Checklist
Build Checklist ¦ PDLC v1.0
Design source: Section 16. Jira administrator. Confirm tenant-specific support before implementation.
Sequence | Admin action | Acceptance evidence
01 | Confirm Jira Cloud edition, enterprise app approvals, company-managed project policy | Tenant capability record
02 | Validate existing global hierarchy; avoid changing without separate approval | Hierarchy review and migration impact
03 | Create/reuse exactly 14 work types under PDLC-ITS-v1 | Work type scheme export/screenshot
04 | Create canonical statuses with correct categories | Status catalogue accepted
05 | Implement 8 workflows, transitions, guards and Resolution handling | Transition tests by work type
06 | Associate workflows in PDLC-WFS-v1 | Matrix matches work types
07 | Reuse/create field catalogue with restricted contexts | Duplicate-field review and field dictionary
08 | Configure Field schemes or legacy Field configurations | Requiredness/visibility tests at creation and gates
09 | Create 15 screens and 8 screen schemes; map PDLC-ITSS-v1 | UI tests by issue type and actor
10 | Configure roles, permissions and issue-security levels | Least-privilege and restricted record tests
11 | Configure priority, components, versions and agreed link types | Link and version search/Plans tests
12 | Implement minimum P0 automations/integrations and observability | Trigger, retry, idempotency, failure tests
13 | Set up board/quality/controls/portfolio views | Stakeholder UAT and source reconciliation
14 | Run end-to-end risk-tier test scripts with human/agent scenarios | Approved evidence pack
15 | Pilot, evaluate, approve and version future iterations | Sponsor decision and change control record